# Effort Estimation & 60-Day Project Plan

This document provides the effort estimation and a 60-day execution plan for the development of a centralized Online Procurement System. The solution will be developed using Angular for the frontend, .NET 9 Web API for the backend, and SQL Server/PostgreSQL for database management.

# 1. Scope & Database Design

- Requirement Refinement & Use Case Finalization: 5–7 days
- Entity-Relationship (ER) Design: 8–10 days
- Database Setup & Migration Scripts: 3–4 days

Total: ~16–20 person-days

# 2. 60-Day Project Plan (One Frontend Dev + One Backend Dev)

The plan is structured into 6 phases. Development will be done in parallel by one frontend developer and one backend developer.

## Phase 1: Foundation (Day 1–10)

Backend: DB schema, EF Core migrations, Authentication/Authorization APIs (JWT).

Frontend: Angular setup, Authentication UI, Role-based layouts.

Deliverable: Working login + role-based navigation, DB in place.

## Phase 2: Vendor Management + Dashboard (Day 11–20)

Backend: Vendor CRUD APIs, performance rating, dashboard API.

Frontend: Vendor onboarding/profile UI, Dashboard UI with charts.

Deliverable: Vendor lifecycle + dashboard with live data.

## Phase 3: RFQ & RFP (Day 21–30)

Backend: RFQ APIs, RFP APIs linked to RFQs.

Frontend: RFQ UI (forms, tracking), RFP creation & evaluation criteria UI.

Deliverable: Procurement manager can raise RFQs/RFPs, vendors can view them.

## Phase 4: Bidding Module (Day 31–40)

Backend: Bid submission APIs, scoring logic, bid comparison service.

Frontend: Bid submission UI for vendors, comparison dashboard for managers.

Deliverable: Vendors submit bids, managers compare & score.

## Phase 5: Purchase Order (Day 41–50)

Backend: PO generation, approval workflow, PO tracking.

Frontend: PO creation, approval, and tracking UI.

Deliverable: Managers can generate & approve POs from bids.

## Phase 6: Invoices, Reports & Notifications (Day 51–60)

Backend: Invoice APIs, basic reports (CSV/PDF), Email notifications.

Frontend: Invoice submission UI, basic reporting view, notifications placeholder.

Deliverable: Invoices handled minimally, reports generated, email notifications available.

# 3. Module Coverage in 60 Days

| Module | Coverage in 60 Days |
| --- | --- |
| Authentication & Authorization | Full |
| Dashboard | Full |
| Vendor Management | Full |
| RFQ | Full |
| RFP | Basic (linked RFQs, criteria) |
| RFI | Skipped (Phase 2) |
| Bidding | Full (except reverse auction → Phase 2) |
| Purchase Order | Full |
| Invoice Management | Full |
| Reporting & Analytics | Basic (CSV/PDF) |
| Notifications | Email only (others Phase 2) |

# 4. Effort Split (Per Developer in 60 Days)

Backend Developer (~60 days):
- DB + Auth + Core APIs: 20 days
- Vendor, RFQ, RFP: 15 days
- Bidding + PO: 15 days
- Invoices + Reports + Notifications: 10 days

Frontend Developer (~60 days):
- Auth & Layouts: 10 days
- Dashboard + Vendor: 15 days
- RFQ & RFP: 15 days
- Bidding + PO: 15 days
- Invoices + Reports + Notifications: 5 days